## Dashboard
Weekly pipeline dashboard
Stage | Units in stage (WIP) | Blocked | Late vs. SLA | Avg days in stage | Rework loops (sum)
1. Brief & Content
2. Script
3. Visual Assets
4. Motion
5. Final Video
Done
Weekly throughput vs. plan (target 30 finished videos / week)
Week | Week starting | Target (cum.) | Finished in week | Finished (cum.) | Gap vs. plan | Required / week to hit 300
1 | 2026-10-05 | 30
2 | 2026-10-12 | 60
3 | 2026-10-19 | 90
4 | 2026-10-26 | 120
5 | 2026-11-02 | 150
6 | 2026-11-09 | 180
7 | 2026-11-16 | 210
8 | 2026-11-23 | 240
9 | 2026-11-30 | 270
10 | 2026-12-07 | 300
Blocked units by reason and stage
Blocker reason | 1. Brief & Content | 2. Script | 3. Visual Assets | 4. Motion | 5. Final Video | Total

## Tracker
Luca – content production master tracker (300 videos / 10 weeks)
As-of date: | 2026-10-09 |  | Teal headers = the 5 key fields. One row per video. The stage owner updates their row every day before the 15-minute stand-up.
Unit ID | Subject | Grade | Tier (A/B/C) | Stage | Accountable owner | Stage start date | Stage due date (SLA) | Days in stage | Days late | Status | Blocker reason | Blocked since | Rework loops | Done date | Target ship week
V-001 | Math | Primaria 6 | B | Done | — |  |  |  |  | Done |  |  | 1 | 2026-10-09 | 1
V-002 | Spanish | Secundaria 3 | A | Done | — |  |  |  |  | Done |  |  | 2 | 2026-10-09 | 1
V-003 | Science | Primaria 4 | A | Done | — |  |  |  |  | Done |  |  | 1 | 2026-10-08 | 1
V-004 | History | Primaria 2 | B | Done | — |  |  |  |  | Done |  |  | 1 | 2026-10-08 | 1
V-005 | English | Primaria 2 | B | Done | — |  |  |  |  | Done |  |  | 1 | 2026-10-08 | 1
V-006 | Geography | Primaria 4 | A | 5. Final Video | Synthesia Specialist 1 | 2026-10-08 |  |  |  | Blocked | Audio / video sync | 2026-10-09 | 0 |  | 1
V-007 | Civics | Secundaria 3 | A | 5. Final Video | Sound Editor 1 | 2026-10-08 |  |  |  | Blocked | Audio / video sync | 2026-10-09 | 0 |  | 1
V-008 | Math | Primaria 4 | B | 5. Final Video | Synthesia Specialist 1 | 2026-10-08 |  |  |  | Blocked | Audio / video sync | 2026-10-09 | 1 |  | 1
V-009 | Spanish | Primaria 1 | B | 4. Motion | Motion Designer 2 | 2026-10-06 |  |  |  | Blocked | Change request after lock | 2026-10-07 | 1 |  | 1
V-010 | Science | Secundaria 2 | C | 4. Motion | Motion Designer 2 | 2026-10-07 |  |  |  | Blocked | Change request after lock | 2026-10-08 | 0 |  | 1
V-011 | History | Primaria 4 | A | 4. Motion | Motion Designer 2 | 2026-10-06 |  |  |  | Blocked | Change request after lock | 2026-10-07 | 1 |  | 1
V-012 | English | Secundaria 2 | B | 4. Motion | Motion Designer 1 | 2026-10-06 |  |  |  | Blocked | Change request after lock | 2026-10-07 | 0 |  | 1
V-013 | Geography | Primaria 6 | B | 4. Motion | Motion Designer 2 | 2026-10-07 |  |  |  | Blocked | Change request after lock | 2026-10-08 | 1 |  | 1
V-014 | Civics | Primaria 2 | B | 4. Motion | Motion Designer 2 | 2026-10-06 |  |  |  | Blocked | Change request after lock | 2026-10-07 | 1 |  | 1
V-015 | Math | Secundaria 2 | C | 4. Motion | Motion Designer 1 | 2026-10-06 |  |  |  | Blocked | Change request after lock | 2026-10-07 | 1 |  | 1
V-016 | Spanish | Primaria 2 | A | 3. Visual Assets | Graphic Designer 2 | 2026-10-07 |  |  |  | Blocked | Waiting for input from previous stage | 2026-10-08 | 1 |  | 1
V-017 | Science | Secundaria 1 | B | 3. Visual Assets | Graphic Designer 1 | 2026-10-07 |  |  |  | Blocked | Waiting for input from previous stage | 2026-10-08 | 0 |  | 1
V-018 | History | Primaria 2 | C | 3. Visual Assets | Graphic Designer 1 | 2026-10-07 |  |  |  | Blocked | Waiting for input from previous stage | 2026-10-08 | 0 |  | 1
V-019 | English | Primaria 4 | C | 3. Visual Assets | Graphic Designer 2 | 2026-10-07 |  |  |  | Blocked | Waiting for input from previous stage | 2026-10-08 | 0 |  | 1
V-020 | Geography | Secundaria 2 | C | 3. Visual Assets | Graphic Designer 2 | 2026-10-07 |  |  |  | Blocked | Waiting for input from previous stage | 2026-10-08 | 1 |  | 1
V-021 | Civics | Primaria 5 | C | 2. Script | Scriptwriter 2 | 2026-10-05 |  |  |  | Blocked | Content misalignment / rework | 2026-10-06 | 2 |  | 1
V-022 | Math | Primaria 3 | A | 2. Script | Scriptwriter 1 | 2026-10-07 |  |  |  | Blocked | Content misalignment / rework | 2026-10-08 | 2 |  | 1
V-023 | Spanish | Primaria 1 | C | 2. Script | Scriptwriter 3 | 2026-10-07 |  |  |  | Blocked | Content misalignment / rework | 2026-10-08 | 2 |  | 1
V-024 | Science | Primaria 1 | B | 2. Script | Scriptwriter 2 | 2026-10-05 |  |  |  | Blocked | Content misalignment / rework | 2026-10-06 | 2 |  | 1
V-025 | History | Primaria 3 | A | 2. Script | Scriptwriter 2 | 2026-10-05 |  |  |  | Blocked | Content misalignment / rework | 2026-10-06 | 3 |  | 1
V-026 | English | Secundaria 1 | C | 2. Script | Scriptwriter 1 | 2026-10-06 |  |  |  | Blocked | Content misalignment / rework | 2026-10-07 | 1 |  | 1
V-027 | Geography | Primaria 4 | A | 2. Script | Scriptwriter 1 | 2026-10-06 |  |  |  | Blocked | Content misalignment / rework | 2026-10-07 | 1 |  | 1
V-028 | Civics | Primaria 6 | A | 2. Script | Scriptwriter 1 | 2026-10-07 |  |  |  | Blocked | Content misalignment / rework | 2026-10-08 | 1 |  | 1
V-029 | Math | Primaria 6 | A | 2. Script | Scriptwriter 1 | 2026-10-07 |  |  |  | Blocked | Content misalignment / rework | 2026-10-08 | 2 |  | 1
V-030 | Spanish | Primaria 5 | B | 2. Script | Scriptwriter 3 | 2026-10-06 |  |  |  | Blocked | Content misalignment / rework | 2026-10-07 | 1 |  | 1
V-031 | Science | Primaria 2 | C | 2. Script | Scriptwriter 2 | 2026-10-06 |  |  |  | Blocked | Content misalignment / rework | 2026-10-07 | 2 |  | 2
V-032 | History | Primaria 2 | B | 2. Script | Scriptwriter 1 | 2026-10-05 |  |  |  | Blocked | Content misalignment / rework | 2026-10-06 | 2 |  | 2
V-033 | English | Secundaria 2 | B | 2. Script | Scriptwriter 3 | 2026-10-07 |  |  |  | Blocked | Content misalignment / rework | 2026-10-08 | 2 |  | 2
V-034 | Geography | Primaria 3 | A | 2. Script | Scriptwriter 3 | 2026-10-06 |  |  |  | Blocked | Content misalignment / rework | 2026-10-07 | 2 |  | 2
V-035 | Civics | Secundaria 3 | B | 2. Script | Scriptwriter 1 | 2026-10-06 |  |  |  | Blocked | Content misalignment / rework | 2026-10-07 | 2 |  | 2
V-036 | [9 empty] | Not started |  |  | 0 |  | 2
V-037 | [9 empty] | Not started |  |  | 0 |  | 2
V-038 | [9 empty] | Not started |  |  | 0 |  | 2
V-039 | [9 empty] | Not started |  |  | 0 |  | 2
V-040 | [9 empty] | Not started |  |  | 0 |  | 2
V-041 | [9 empty] | Not started |  |  | 0 |  | 2
V-042 | [9 empty] | Not started |  |  | 0 |  | 2
V-043 | [9 empty] | Not started |  |  | 0 |  | 2
V-044 | [9 empty] | Not started |  |  | 0 |  | 2
V-045 | [9 empty] | Not started |  |  | 0 |  | 2
V-046 | [9 empty] | Not started |  |  | 0 |  | 2
V-047 | [9 empty] | Not started |  |  | 0 |  | 2
V-048 | [9 empty] | Not started |  |  | 0 |  | 2
V-049 | [9 empty] | Not started |  |  | 0 |  | 2
V-050 | [9 empty] | Not started |  |  | 0 |  | 2
V-051 | [9 empty] | Not started |  |  | 0 |  | 2
V-052 | [9 empty] | Not started |  |  | 0 |  | 2
V-053 | [9 empty] | Not started |  |  | 0 |  | 2
V-054 | [9 empty] | Not started |  |  | 0 |  | 2
V-055 | [9 empty] | Not started |  |  | 0 |  | 2
V-056 | [9 empty] | Not started |  |  | 0 |  | 2
V-057 | [9 empty] | Not started |  |  | 0 |  | 2
V-058 | [9 empty] | Not started |  |  | 0 |  | 2
V-059 | [9 empty] | Not started |  |  | 0 |  | 2
V-060 | [9 empty] | Not started |  |  | 0 |  | 2
V-061 | [9 empty] | Not started |  |  | 0 |  | 3
V-062 | [9 empty] | Not started |  |  | 0 |  | 3
V-063 | [9 empty] | Not started |  |  | 0 |  | 3
V-064 | [9 empty] | Not started |  |  | 0 |  | 3
V-065 | [9 empty] | Not started |  |  | 0 |  | 3
V-066 | [9 empty] | Not started |  |  | 0 |  | 3
V-067 | [9 empty] | Not started |  |  | 0 |  | 3
V-068 | [9 empty] | Not started |  |  | 0 |  | 3
V-069 | [9 empty] | Not started |  |  | 0 |  | 3
V-070 | [9 empty] | Not started |  |  | 0 |  | 3
V-071 | [9 empty] | Not started |  |  | 0 |  | 3
V-072 | [9 empty] | Not started |  |  | 0 |  | 3
V-073 | [9 empty] | Not started |  |  | 0 |  | 3
V-074 | [9 empty] | Not started |  |  | 0 |  | 3
V-075 | [9 empty] | Not started |  |  | 0 |  | 3
V-076 | [9 empty] | Not started |  |  | 0 |  | 3
V-077 | [9 empty] | Not started |  |  | 0 |  | 3
V-078 | [9 empty] | Not started |  |  | 0 |  | 3
V-079 | [9 empty] | Not started |  |  | 0 |  | 3
V-080 | [9 empty] | Not started |  |  | 0 |  | 3
V-081 | [9 empty] | Not started |  |  | 0 |  | 3
V-082 | [9 empty] | Not started |  |  | 0 |  | 3
V-083 | [9 empty] | Not started |  |  | 0 |  | 3
V-084 | [9 empty] | Not started |  |  | 0 |  | 3
V-085 | [9 empty] | Not started |  |  | 0 |  | 3
V-086 | [9 empty] | Not started |  |  | 0 |  | 3
V-087 | [9 empty] | Not started |  |  | 0 |  | 3
V-088 | [9 empty] | Not started |  |  | 0 |  | 3
V-089 | [9 empty] | Not started |  |  | 0 |  | 3
V-090 | [9 empty] | Not started |  |  | 0 |  | 3
V-091 | [9 empty] | Not started |  |  | 0 |  | 4
V-092 | [9 empty] | Not started |  |  | 0 |  | 4
V-093 | [9 empty] | Not started |  |  | 0 |  | 4
V-094 | [9 empty] | Not started |  |  | 0 |  | 4
V-095 | [9 empty] | Not started |  |  | 0 |  | 4
V-096 | [9 empty] | Not started |  |  | 0 |  | 4
V-097 | [9 empty] | Not started |  |  | 0 |  | 4
V-098 | [9 empty] | Not started |  |  | 0 |  | 4
V-099 | [9 empty] | Not started |  |  | 0 |  | 4
V-100 | [9 empty] | Not started |  |  | 0 |  | 4
V-101 | [9 empty] | Not started |  |  | 0 |  | 4
V-102 | [9 empty] | Not started |  |  | 0 |  | 4
V-103 | [9 empty] | Not started |  |  | 0 |  | 4
V-104 | [9 empty] | Not started |  |  | 0 |  | 4
V-105 | [9 empty] | Not started |  |  | 0 |  | 4
V-106 | [9 empty] | Not started |  |  | 0 |  | 4
V-107 | [9 empty] | Not started |  |  | 0 |  | 4
V-108 | [9 empty] | Not started |  |  | 0 |  | 4
V-109 | [9 empty] | Not started |  |  | 0 |  | 4
V-110 | [9 empty] | Not started |  |  | 0 |  | 4
V-111 | [9 empty] | Not started |  |  | 0 |  | 4
V-112 | [9 empty] | Not started |  |  | 0 |  | 4
V-113 | [9 empty] | Not started |  |  | 0 |  | 4
V-114 | [9 empty] | Not started |  |  | 0 |  | 4
V-115 | [9 empty] | Not started |  |  | 0 |  | 4
V-116 | [9 empty] | Not started |  |  | 0 |  | 4
V-117 | [9 empty] | Not started |  |  | 0 |  | 4
V-118 | [9 empty] | Not started |  |  | 0 |  | 4
V-119 | [9 empty] | Not started |  |  | 0 |  | 4
V-120 | [9 empty] | Not started |  |  | 0 |  | 4
V-121 | [9 empty] | Not started |  |  | 0 |  | 5
V-122 | [9 empty] | Not started |  |  | 0 |  | 5
V-123 | [9 empty] | Not started |  |  | 0 |  | 5
V-124 | [9 empty] | Not started |  |  | 0 |  | 5
V-125 | [9 empty] | Not started |  |  | 0 |  | 5
V-126 | [9 empty] | Not started |  |  | 0 |  | 5
V-127 | [9 empty] | Not started |  |  | 0 |  | 5
V-128 | [9 empty] | Not started |  |  | 0 |  | 5
V-129 | [9 empty] | Not started |  |  | 0 |  | 5
V-130 | [9 empty] | Not started |  |  | 0 |  | 5
V-131 | [9 empty] | Not started |  |  | 0 |  | 5
V-132 | [9 empty] | Not started |  |  | 0 |  | 5
V-133 | [9 empty] | Not started |  |  | 0 |  | 5
V-134 | [9 empty] | Not started |  |  | 0 |  | 5
V-135 | [9 empty] | Not started |  |  | 0 |  | 5
V-136 | [9 empty] | Not started |  |  | 0 |  | 5
V-137 | [9 empty] | Not started |  |  | 0 |  | 5
V-138 | [9 empty] | Not started |  |  | 0 |  | 5
V-139 | [9 empty] | Not started |  |  | 0 |  | 5
V-140 | [9 empty] | Not started |  |  | 0 |  | 5
V-141 | [9 empty] | Not started |  |  | 0 |  | 5
V-142 | [9 empty] | Not started |  |  | 0 |  | 5
V-143 | [9 empty] | Not started |  |  | 0 |  | 5
V-144 | [9 empty] | Not started |  |  | 0 |  | 5
V-145 | [9 empty] | Not started |  |  | 0 |  | 5
V-146 | [9 empty] | Not started |  |  | 0 |  | 5
V-147 | [9 empty] | Not started |  |  | 0 |  | 5
V-148 | [9 empty] | Not started |  |  | 0 |  | 5
V-149 | [9 empty] | Not started |  |  | 0 |  | 5
V-150 | [9 empty] | Not started |  |  | 0 |  | 5
V-151 | [9 empty] | Not started |  |  | 0 |  | 6
V-152 | [9 empty] | Not started |  |  | 0 |  | 6
V-153 | [9 empty] | Not started |  |  | 0 |  | 6
V-154 | [9 empty] | Not started |  |  | 0 |  | 6
V-155 | [9 empty] | Not started |  |  | 0 |  | 6
V-156 | [9 empty] | Not started |  |  | 0 |  | 6
V-157 | [9 empty] | Not started |  |  | 0 |  | 6
V-158 | [9 empty] | Not started |  |  | 0 |  | 6
V-159 | [9 empty] | Not started |  |  | 0 |  | 6
V-160 | [9 empty] | Not started |  |  | 0 |  | 6
V-161 | [9 empty] | Not started |  |  | 0 |  | 6
V-162 | [9 empty] | Not started |  |  | 0 |  | 6
V-163 | [9 empty] | Not started |  |  | 0 |  | 6
V-164 | [9 empty] | Not started |  |  | 0 |  | 6
V-165 | [9 empty] | Not started |  |  | 0 |  | 6
V-166 | [9 empty] | Not started |  |  | 0 |  | 6
V-167 | [9 empty] | Not started |  |  | 0 |  | 6
V-168 | [9 empty] | Not started |  |  | 0 |  | 6
V-169 | [9 empty] | Not started |  |  | 0 |  | 6
V-170 | [9 empty] | Not started |  |  | 0 |  | 6
V-171 | [9 empty] | Not started |  |  | 0 |  | 6
V-172 | [9 empty] | Not started |  |  | 0 |  | 6
V-173 | [9 empty] | Not started |  |  | 0 |  | 6
V-174 | [9 empty] | Not started |  |  | 0 |  | 6
V-175 | [9 empty] | Not started |  |  | 0 |  | 6
V-176 | [9 empty] | Not started |  |  | 0 |  | 6
V-177 | [9 empty] | Not started |  |  | 0 |  | 6
V-178 | [9 empty] | Not started |  |  | 0 |  | 6
V-179 | [9 empty] | Not started |  |  | 0 |  | 6
V-180 | [9 empty] | Not started |  |  | 0 |  | 6
V-181 | [9 empty] | Not started |  |  | 0 |  | 7
V-182 | [9 empty] | Not started |  |  | 0 |  | 7
V-183 | [9 empty] | Not started |  |  | 0 |  | 7
V-184 | [9 empty] | Not started |  |  | 0 |  | 7
V-185 | [9 empty] | Not started |  |  | 0 |  | 7
V-186 | [9 empty] | Not started |  |  | 0 |  | 7
V-187 | [9 empty] | Not started |  |  | 0 |  | 7
V-188 | [9 empty] | Not started |  |  | 0 |  | 7
V-189 | [9 empty] | Not started |  |  | 0 |  | 7
V-190 | [9 empty] | Not started |  |  | 0 |  | 7
V-191 | [9 empty] | Not started |  |  | 0 |  | 7
V-192 | [9 empty] | Not started |  |  | 0 |  | 7
V-193 | [9 empty] | Not started |  |  | 0 |  | 7
V-194 | [9 empty] | Not started |  |  | 0 |  | 7
V-195 | [9 empty] | Not started |  |  | 0 |  | 7
V-196 | [9 empty] | Not started |  |  | 0 |  | 7
V-197 | [9 empty] | Not started |  |  | 0 |  | 7
V-198 | [9 empty] | Not started |  |  | 0 |  | 7
V-199 | [9 empty] | Not started |  |  | 0 |  | 7
V-200 | [9 empty] | Not started |  |  | 0 |  | 7
V-201 | [9 empty] | Not started |  |  | 0 |  | 7
V-202 | [9 empty] | Not started |  |  | 0 |  | 7
V-203 | [9 empty] | Not started |  |  | 0 |  | 7
V-204 | [9 empty] | Not started |  |  | 0 |  | 7
V-205 | [9 empty] | Not started |  |  | 0 |  | 7
V-206 | [9 empty] | Not started |  |  | 0 |  | 7
V-207 | [9 empty] | Not started |  |  | 0 |  | 7
V-208 | [9 empty] | Not started |  |  | 0 |  | 7
V-209 | [9 empty] | Not started |  |  | 0 |  | 7
V-210 | [9 empty] | Not started |  |  | 0 |  | 7
V-211 | [9 empty] | Not started |  |  | 0 |  | 8
V-212 | [9 empty] | Not started |  |  | 0 |  | 8
V-213 | [9 empty] | Not started |  |  | 0 |  | 8
V-214 | [9 empty] | Not started |  |  | 0 |  | 8
V-215 | [9 empty] | Not started |  |  | 0 |  | 8
V-216 | [9 empty] | Not started |  |  | 0 |  | 8
V-217 | [9 empty] | Not started |  |  | 0 |  | 8
V-218 | [9 empty] | Not started |  |  | 0 |  | 8
V-219 | [9 empty] | Not started |  |  | 0 |  | 8
V-220 | [9 empty] | Not started |  |  | 0 |  | 8
V-221 | [9 empty] | Not started |  |  | 0 |  | 8
V-222 | [9 empty] | Not started |  |  | 0 |  | 8
V-223 | [9 empty] | Not started |  |  | 0 |  | 8
V-224 | [9 empty] | Not started |  |  | 0 |  | 8
V-225 | [9 empty] | Not started |  |  | 0 |  | 8
V-226 | [9 empty] | Not started |  |  | 0 |  | 8
V-227 | [9 empty] | Not started |  |  | 0 |  | 8
V-228 | [9 empty] | Not started |  |  | 0 |  | 8
V-229 | [9 empty] | Not started |  |  | 0 |  | 8
V-230 | [9 empty] | Not started |  |  | 0 |  | 8
V-231 | [9 empty] | Not started |  |  | 0 |  | 8
V-232 | [9 empty] | Not started |  |  | 0 |  | 8
V-233 | [9 empty] | Not started |  |  | 0 |  | 8
V-234 | [9 empty] | Not started |  |  | 0 |  | 8
V-235 | [9 empty] | Not started |  |  | 0 |  | 8
V-236 | [9 empty] | Not started |  |  | 0 |  | 8
V-237 | [9 empty] | Not started |  |  | 0 |  | 8
V-238 | [9 empty] | Not started |  |  | 0 |  | 8
V-239 | [9 empty] | Not started |  |  | 0 |  | 8
V-240 | [9 empty] | Not started |  |  | 0 |  | 8
V-241 | [9 empty] | Not started |  |  | 0 |  | 9
V-242 | [9 empty] | Not started |  |  | 0 |  | 9
V-243 | [9 empty] | Not started |  |  | 0 |  | 9
V-244 | [9 empty] | Not started |  |  | 0 |  | 9
V-245 | [9 empty] | Not started |  |  | 0 |  | 9
V-246 | [9 empty] | Not started |  |  | 0 |  | 9
V-247 | [9 empty] | Not started |  |  | 0 |  | 9
V-248 | [9 empty] | Not started |  |  | 0 |  | 9
V-249 | [9 empty] | Not started |  |  | 0 |  | 9
V-250 | [9 empty] | Not started |  |  | 0 |  | 9
V-251 | [9 empty] | Not started |  |  | 0 |  | 9
V-252 | [9 empty] | Not started |  |  | 0 |  | 9
V-253 | [9 empty] | Not started |  |  | 0 |  | 9
V-254 | [9 empty] | Not started |  |  | 0 |  | 9
V-255 | [9 empty] | Not started |  |  | 0 |  | 9
V-256 | [9 empty] | Not started |  |  | 0 |  | 9
V-257 | [9 empty] | Not started |  |  | 0 |  | 9
V-258 | [9 empty] | Not started |  |  | 0 |  | 9
V-259 | [9 empty] | Not started |  |  | 0 |  | 9
V-260 | [9 empty] | Not started |  |  | 0 |  | 9
V-261 | [9 empty] | Not started |  |  | 0 |  | 9
V-262 | [9 empty] | Not started |  |  | 0 |  | 9
V-263 | [9 empty] | Not started |  |  | 0 |  | 9
V-264 | [9 empty] | Not started |  |  | 0 |  | 9
V-265 | [9 empty] | Not started |  |  | 0 |  | 9
V-266 | [9 empty] | Not started |  |  | 0 |  | 9
V-267 | [9 empty] | Not started |  |  | 0 |  | 9
V-268 | [9 empty] | Not started |  |  | 0 |  | 9
V-269 | [9 empty] | Not started |  |  | 0 |  | 9
V-270 | [9 empty] | Not started |  |  | 0 |  | 9
V-271 | [9 empty] | Not started |  |  | 0 |  | 10
V-272 | [9 empty] | Not started |  |  | 0 |  | 10
V-273 | [9 empty] | Not started |  |  | 0 |  | 10
V-274 | [9 empty] | Not started |  |  | 0 |  | 10
V-275 | [9 empty] | Not started |  |  | 0 |  | 10
V-276 | [9 empty] | Not started |  |  | 0 |  | 10
V-277 | [9 empty] | Not started |  |  | 0 |  | 10
V-278 | [9 empty] | Not started |  |  | 0 |  | 10
V-279 | [9 empty] | Not started |  |  | 0 |  | 10
V-280 | [9 empty] | Not started |  |  | 0 |  | 10
V-281 | [9 empty] | Not started |  |  | 0 |  | 10
V-282 | [9 empty] | Not started |  |  | 0 |  | 10
V-283 | [9 empty] | Not started |  |  | 0 |  | 10
V-284 | [9 empty] | Not started |  |  | 0 |  | 10
V-285 | [9 empty] | Not started |  |  | 0 |  | 10
V-286 | [9 empty] | Not started |  |  | 0 |  | 10
V-287 | [9 empty] | Not started |  |  | 0 |  | 10
V-288 | [9 empty] | Not started |  |  | 0 |  | 10
V-289 | [9 empty] | Not started |  |  | 0 |  | 10
V-290 | [9 empty] | Not started |  |  | 0 |  | 10
V-291 | [9 empty] | Not started |  |  | 0 |  | 10
V-292 | [9 empty] | Not started |  |  | 0 |  | 10
V-293 | [9 empty] | Not started |  |  | 0 |  | 10
V-294 | [9 empty] | Not started |  |  | 0 |  | 10
V-295 | [9 empty] | Not started |  |  | 0 |  | 10
V-296 | [9 empty] | Not started |  |  | 0 |  | 10
V-297 | [9 empty] | Not started |  |  | 0 |  | 10
V-298 | [9 empty] | Not started |  |  | 0 |  | 10
V-299 | [9 empty] | Not started |  |  | 0 |  | 10
V-300 | [9 empty] | Not started |  |  | 0 |  | 10

## Lists
Stage | SLA (days) | Blocker reasons
1. Brief & Content | 1 | Content misalignment / rework
2. Script | 2 | Waiting for input from previous stage
3. Visual Assets | 1 | Change request after lock
4. Motion | 2 | Audio / video sync
5. Final Video | 2 | Capacity / not started
Tool / technical issue