## Slide 1
1 · QUICK DIAGNOSIS OF WEEK 1
We finished 5 of 30 videos: rework in scripting and change churn in motion are choking the line
Luca · Chief of Staff hiring case · all data fictional | Source: outgoing PMO Week 1 tracking
1
Units started vs. finished by stage (bar = 35 units)
1. Brief & content definition
Content Authors
35/35
100%
finished
1 h/unit · 0 blocked
—
2. Script creation & review
Scriptwriters
20/35
57%
finished
4 h/unit · 15 blocked
Misalignment with authors; heavy rework
#1
3. Visual asset design
Graphic Designers
15/20
75%
finished
3 h/unit · 5 blocked
Waiting for final script
4. Motion graphics & animation
Motion Designers
8/15
53%
finished
5 h/unit · 7 blocked
Frequent changes from earlier stages
#2
5. Final video (Synthesia + sound)
Synthesia / Sound
5/8
62%
finished
6 h/unit · 3 blocked
A/V sync; last-minute visual tweaks
WEEK 1 OUTPUT
5 / 30
17% of weekly target
NEEDED W2–W10
32.8 / week
to still deliver 300 by Week 10
STUCK IN PROGRESS
30 units
19 touch-hours per finished video
#1 Script creation & review (Stage 2)
• Evidence: 15 of 35 units (43%) stuck, the largest loss in the line. It also starves Stage 3, where 5 units are waiting for a final script.
• Root cause: no shared 'definition of ready' between Content Authors and Scriptwriters. Reviews happen one after another, so each misunderstanding means a full rewrite (4 h/unit).
• So what: at most 20 scripts a week can enter production, so 30 a week is impossible upstream.
#2 Motion graphics & animation (Stage 4)
• Evidence: lowest completion rate (53%, 8 of 15) and the most effort of any creative stage (5 h/unit). 7 units are blocked by changes from earlier stages.
• Root cause: no freeze point. Script and visual edits keep arriving after animation has started, and every video is animated from scratch.
• So what: only 8 units reach final assembly. At target pace motion needs ~150 h/week; it lost a big part of Week 1 to redoing work.
Common thread: changes flow downstream unchecked, and Stage 1 keeps starting work the line can't absorb.

## Slide 2
1 · 2-WEEK ACTION PLAN
Five rules for the next 2 weeks: align upstream, freeze changes, limit WIP, add motion capacity
Luca · Chief of Staff hiring case · all data fictional | Targets are commitments to review in the weekly pipeline meeting
2
# | Action (decision / rule we put in place) | Owner | When | Success metric (end of Week 3)
1 | One brief, co-signed. The Content Author and Scriptwriter fill in a 1-page 'script-ready brief' in a 20-min pairing before any script starts: learning objective, key concepts, scene outline, 600–850 words. Author reviews within 24 h, max 2 rounds; a 3rd round goes to the Curriculum Lead to decide. | Head of Content Ops | Day 1–2 | ≥80% scripts approved first pass; ≤1.2 rework loops / unit
2 | Lock points + change control. The script locks when it leaves Stage 2 and visuals lock when they leave Stage 4. After a lock, only factual or pedagogical errors may change (Content Lead approves within 24 h). Everything else goes to a v2 backlog. | Curriculum Lead | Day 1 | 0 change-driven blockers in Stages 4–5
3 | Stop starting, start finishing. Cap the queue in front of each stage at 10 units. Stage 1 pauses new briefs while the script queue is over 10. Authors spend 50% of their time in pair-fix sessions to clear the 15 blocked scripts. | PMO / Chief of Staff | Day 1–5 | Script backlog 15 → <5; WIP ≤ 40 units
4 | Add capacity where it's scarce. 3 complexity tiers (A bespoke 20% · B template 50% · C avatar + static 30%). A library of 15–20 reusable motion templates. 2–3 freelance motion designers for W2–W6. Designers start from the approved scene outline, in parallel with the script. | Motion Lead + Head of Content Ops | Week 1–2 | Motion 5.0 → ≤3.0 h/unit; ≥36 units/week out of Stage 4
5 | Right-first-time final assembly. One technical spec (audio −16 LUFS, 48 kHz, timings from the locked script), a Synthesia template per subject, sound + Synthesia working as one cell on the same batch, and a 10-point QC checklist before export. | Synthesia Lead | Week 2 | 0 A/V sync rejects; Stage 5 6 → 4 h/unit
Chart: Cumulative finished videos
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Original plan (30/wk) | 30 | 60 | 90 | 120 | 150 | 180 | 210 | 240 | 270 | 300
Recovery plan | 5 | 20 | 45 | 81 | 117 | 154 | 190 | 227 | 263 | 300
Weekly finish targets
W2: 15 · W3: 25 · W4–W10: ≥36/week → 300 by Week 10.
W2 mostly clears the 30 units already in progress; from W4 the tiers and templates carry the higher pace.
Escalation rule: if W3 is under 20, the steering group moves more videos to Tier C and orders subjects by the school-term calendar.

## Slide 3
1 · AI VIDEO PRODUCTION TOOL & ARCHITECTURE
One AI-orchestrated pipeline from curriculum to finished video, with humans approving at key gates
Luca · Chief of Staff hiring case · all data fictional | Hour savings are planning estimates to validate in the MVP
3
KNOWLEDGE LAYER (RAG) SEP curriculum & learning objectives · Luca lesson library & pedagogy style guide · brand/asset & motion-template library · performance data (watch time, quiz results)
1. Brief agent
LLM + RAG drafts objective, concepts, misconceptions, scene outline
Author approves
Effort/unit: 1.0 → 0.3 h
2. Script agent + QA
Writes in Luca template; auto-checks length, reading level, accuracy, safety
Scriptwriter edits & locks
Effort/unit: 4.0 → 1.5 h
3. Scene spec (JSON)
Per scene: narration, on-screen text, visual prompt, template ID, duration
Single source of truth
Effort/unit: auto
4. Visual assets
Reuse library first; generate brand-styled images; diagrams & math as code
Designer curates
Effort/unit: 3.0 → 1.5 h
5. Motion renderer
Fills motion templates from scene JSON; bespoke only for Tier A
Motion designer polishes
Effort/unit: 5.0 → 2.0 h
6. Avatar, voice & finish
Synthesia API render, voice-over, music, loudness, captions, sync check
Final QA sign-off
Effort/unit: 6.0 → 2.0 h
Layer | Engine & sourcing (buy best-of-breed APIs, build only the thin orchestration layer)
LLMs: brief, script, QA | Claude for long-form pedagogy in Spanish & Portuguese; GPT / Gemini through a model router for structured JSON and second-opinion QA. pgvector RAG over the curriculum; 50 gold scripts as eval set.
Visual assets | Adobe Firefly / Ideogram / Flux (commercially safe image generation) with brand style presets; SVG + Manim for diagrams and math; Figma asset library.
Motion | Remotion (programmatic React video) or After Effects templates rendered via Nexrender / Plainly from the scene JSON; Runway / Veo for short B-roll clips.
Avatar, voice, sound | Synthesia API (current tool, Luca avatars); ElevenLabs for voice-over and LatAm dubbing; licensed music API; ffmpeg loudness (EBU R128); Whisper captions + script-vs-audio sync check.
Orchestration & tracking | n8n for the MVP → Temporal at scale; status written to the master tracker via API; review UI in Lovable / Retool with comments per scene; S3 storage with versioning.
Impact, guardrails & prototype
• ≈19 h → ~7 h of human effort per video (−60%), so the same team can deliver 2–3× the output.
• Guardrails: human sign-off on brief and final; child-safety, bias and accuracy checks; an IP/licence log per asset; cost per video tracked.
• Prototype: no link in this version. I propose a 2-week MVP (Lovable front end + Claude API): topic → brief → script → scene JSON → Synthesia draft, piloted on Primaria Math.

## Slide 4
2 · TRACKING & OPERATING RHYTHM
Every Friday we know whether we're on track: one tracker, five fields, three meetings
Luca · Chief of Staff hiring case · all data fictional | Template: Luca_Content_Pipeline_Master_Tracker.xlsx (pre-loaded with the Week 1 snapshot)
4
Master tracker: 5 key fields beyond Unit ID & Stage
Field | What it captures | How it spots delays / drives accountability
1. Accountable owner | One named person for the unit's current stage | No shared ownership: every late unit has a name attached, and the stand-up goes owner by owner.
2. Stage due date (SLA) | Stage start + SLA (e.g. Script 2 days, Motion 2 days) | Auto-calculates 'days late'; red the moment a unit misses its SLA, not at week end.
3. Days in stage | Today − stage start date (aging) | Shows silent stalls before anyone flags a blocker; >2 days turns amber.
4. Status + blocker reason | On track / At risk / Blocked + a standard reason list (e.g. content misalignment, change after lock, A/V sync) | Blockers by reason × stage show the system's failure modes; blocked >24 h is escalated.
5. Rework loops | Number of times the unit was sent back to an earlier stage | Measures quality at hand-offs; ≥2 loops triggers a root-cause look in the weekly review.
Weekly scoreboard (auto, in the tracker): finished vs. 30 target, cumulative vs. plan, run-rate needed to hit 300, WIP and blockers per stage, average days in stage.
Weekly operating rhythm (3 recurring meetings)
Daily production stand-up
Mon–Fri · 15 min
Who: Stage leads (content, script, design, motion, Synthesia/sound) + PMO
Reviews: Walk the board right-to-left (closest to done first): units blocked >24 h, queues over the WIP limit, late units.
Decides: Who unblocks what today; capacity swaps between stages; escalations to the Curriculum Lead.
Weekly pipeline review
Monday · 45 min
Who: Chief of Staff (chair), Head of Content Ops, Curriculum Lead, all stage leads
Reviews: Throughput vs. plan, cycle time per stage, rework rate, top blocker reasons, change requests, next week's capacity.
Decides: Weekly finish commitment per stage; WIP limits; tier mix; approve/deny post-lock changes; freelance hours.
Bi-weekly steering
Every other Thursday · 30 min
Who: CEO / COO, Head of Product / Content, Chief of Staff
Reviews: Forecast to 300 vs. term start, budget vs. actual, AI tool MVP progress, risks.
Decides: Scope trade-offs (subject priority, Tier C share), budget for capacity, AI tool go/no-go.
Plus a Friday 1-page status note (not a meeting) to leadership: on track / at risk, top 3 risks, asks.